## Projects
Project_ID | Project_Name | Department | Project_Type | Region | Project_Manager | Sponsor | Strategic_Theme | Budget_EUR | Forecast_At_Completion_EUR | Baseline_Start | Baseline_End | Forecast_End | Change_Requests | Open_Risks | Planned_Annual_Savings_EUR | Forecast_Annual_Savings_EUR | Realized_Savings_YTD_EUR | Benefit_Tracking_Start | Benefit_Tracking_End | Benefit_Validated | Last_Updated | Reported_RAG | Status_Comment
P01 | Invoice Matching Automation | Procure to Pay | RPA Automation | Europe | Lena Vogel | Henrik Dahl | Cost Reduction | 180000 | 176400 | 2025-05-05 | 2026-11-30 | 2026-11-30 | 2 | 1 | 240000 | 240000 | 122400 | 2026-04-01 | 2027-03-31 | Y | 2026-09-26 | Green | Wave 1 live in 3 countries; wave 2 on plan.
P02 | Billing Error Detection Bot | Billing | RPA Automation | AMER | Rahul Menon | Carla Mendes | Data Quality | 220000 | 226600 | 2025-06-16 | 2026-12-04 | 2026-12-09 | 3 | 1 | 300000 | 285000 | 121500 | 2026-05-01 | 2027-04-30 | Y | 2026-09-24 | Green | Minor test delay; no cost impact.
P03 | Customer Credit Note Automation | Order to Cash | RPA Automation | APAC | Wei Tan | Priya Iyer | Cost Reduction | 150000 | 163500 | 2025-07-07 | 2026-11-13 | 2026-11-25 | 5 | 3 | 200000 | 170000 | 51900 | 2026-06-01 | 2027-05-31 | N | 2026-09-17 | Green | Scope grew after APAC tax review.
P04 | PPM Tool Rollout - Wave 1 | Reporting & Controlling | Tool Rollout | Global | Sofia Almeida | Jonas Keller | Digitalization | 520000 | 540800 | 2025-04-07 | 2027-01-29 | 2027-02-04 | 4 | 2 | 350000 | 340000 | 82200 | 2026-07-01 | 2027-06-30 | Y | 2026-09-29 | Green | Pilot departments onboarded; training on schedule.
P05 | Time Registration Standardisation | Reporting & Controlling | Process Harmonization | Europe | Marcus Bell | Jonas Keller | Compliance | 140000 | 141400 | 2025-08-04 | 2026-12-18 | 2026-12-18 | 1 | 1 | 120000 | 118000 | 39900 | 2026-06-01 | 2027-05-31 | Y | 2026-09-30 | Green | Weekly timesheet deadline agreed with department heads.
P06 | Month-End Close Harmonisation | Financial Accounting | Process Harmonization | Global | Sofia Almeida | Elena Rossi | Compliance | 260000 | 278200 | 2025-05-19 | 2027-01-15 | 2027-02-04 | 6 | 3 | 310000 | 300000 | 46000 | 2026-08-01 | 2027-07-31 | N | 2026-09-21 | Amber | Two regions still on legacy close calendar.
P07 | Cash Application Automation | Order to Cash | RPA Automation | MEA | Rahul Menon | Priya Iyer | Cost Reduction | 190000 | 224200 | 2025-06-23 | 2026-09-18 | 2026-10-13 | 7 | 5 | 280000 | 240000 | 51200 | 2026-06-01 | 2027-05-31 | N | 2026-08-04 | Amber | Bank file formats differ by country; extra mapping work.
P08 | Vendor Master Data Cleanup | Procure to Pay | Process Harmonization | APAC | Wei Tan | Henrik Dahl | Data Quality | 110000 | 112200 | 2025-07-14 | 2026-12-11 | 2026-12-20 | 2 | 2 | 90000 | 90000 | 36800 | 2026-05-01 | 2027-04-30 | Y | 2026-09-25 | Amber | Duplicate vendor review slower than planned.
P09 | Expense Reporting Tool Rollout | Financial Accounting | Tool Rollout | AMER | Lena Vogel | Elena Rossi | Digitalization | 430000 | 481600 | 2025-05-12 | 2027-02-26 | 2027-03-26 | 8 | 4 | 400000 | 360000 | 0 | 2026-11-01 | 2027-10-31 | N | 2026-09-08 | Green | Vendor config delays; go-live still targeted Q4.
P10 | Billing Dispute Workflow | Billing | Tool Rollout | Europe | Marcus Bell | Carla Mendes | Cost Reduction | 340000 | 414800 | 2025-04-28 | 2026-08-31 | 2026-11-04 | 11 | 6 | 420000 | 290000 | 0 | 2026-11-01 | 2027-10-31 | N | 2026-08-18 | Amber | Integration with billing system re-planned.
P11 | Intercompany Reconciliation Automation | Financial Accounting | RPA Automation | Europe | Sofia Almeida | Elena Rossi | Cost Reduction | 275000 | 275000 | 2025-06-09 | 2026-12-04 | 2026-12-04 | 2 | 1 | 360000 | 360000 | 221200 | 2026-03-01 | 2027-02-28 | Y | 2026-09-29 | Green | Ahead on reconciliation match rate.
P12 | Global Reporting Dashboard Refresh | Reporting & Controlling | Tool Rollout | Global | Rahul Menon | Jonas Keller | Digitalization | 200000 | 212000 | 2025-07-21 | 2026-11-20 | 2026-11-30 | 4 | 2 | 150000 | 140000 | 42400 | 2026-06-01 | 2027-05-31 | N | 2026-09-12 | Green | Data refresh issue under review; fix due next sprint.
P13 | Tax Code Harmonisation | Billing | Process Harmonization | MEA | Wei Tan | Carla Mendes | Compliance | 310000 | 341000 | 2025-05-26 | 2026-09-15 | 2026-10-30 | 9 | 5 | 260000 | 240000 | 0 | 2027-01-01 | 2027-12-31 | N | 2026-09-02 | Red | Local tax rules differ more than expected.
P14 | Freight Invoice Audit Automation | Procure to Pay | RPA Automation | AMER | Marcus Bell | Henrik Dahl | Cost Reduction | 240000 | 232800 | 2025-06-30 | 2026-11-27 | 2026-11-27 | 2 | 1 | 330000 | 330000 | 208600 | 2026-03-01 | 2027-02-28 | Y | 2026-09-28 | Green | Audit hit rate above plan.
P15 | Accruals Forecasting Model | Reporting & Controlling | Tool Rollout | Europe | Lena Vogel | Elena Rossi | Data Quality | 160000 | 166400 | 2025-08-18 | 2026-12-10 | 2026-12-14 | 3 | 2 | 210000 | 150000 | 23600 | 2026-07-01 | 2027-06-30 | N | 2026-09-27 | Red | Forecast accuracy below business case; model rework.

## Monthly
Month | Project_ID | Planned_Spend_EUR | Actual_Spend_EUR | Hours_Allocated | Hours_Logged
2025-10-01 | P01 | 6700 | 6400 | 384 | 381
2025-11-01 | P01 | 8500 | 8100 | 432 | 435
2025-12-01 | P01 | 10300 | 9900 | 480 | 500
2026-01-01 | P01 | 12200 | 12200 | 480 | 496
2026-02-01 | P01 | 13400 | 12700 | 480 | 484
2026-03-01 | P01 | 13400 | 11700 | 480 | 498
2026-04-01 | P01 | 13400 | 13100 | 480 | 506
2026-05-01 | P01 | 13400 | 12600 | 480 | 475
2026-06-01 | P01 | 12800 | 12100 | 480 | 506
2026-07-01 | P01 | 12200 | 11800 | 480 | 502
2026-08-01 | P01 | 12200 | 11800 | 480 | 488
2026-09-01 | P01 | 12200 | 12500 | 480 | 481
2025-10-01 | P02 | 8400 | 9200 | 320 | 319
2025-11-01 | P02 | 10700 | 11000 | 360 | 353
2025-12-01 | P02 | 13000 | 13900 | 400 | 400
2026-01-01 | P02 | 15200 | 16200 | 400 | 390
2026-02-01 | P02 | 16800 | 18400 | 400 | 395
2026-03-01 | P02 | 16800 | 16400 | 400 | 373
2026-04-01 | P02 | 16800 | 18200 | 400 | 379
2026-05-01 | P02 | 16800 | 16000 | 400 | 381
2026-06-01 | P02 | 16000 | 14800 | 400 | 375
2026-07-01 | P02 | 15200 | 15400 | 400 | 379
2026-08-01 | P02 | 15200 | 15100 | 400 | 375
2026-09-01 | P02 | 15200 | 16800 | 400 | 381
2025-10-01 | P03 | 5900 | 6000 | 256 | 235
2025-11-01 | P03 | 7500 | 7600 | 288 | 257
2025-12-01 | P03 | 9100 | 9400 | 320 | 283
2026-01-01 | P03 | 10600 | 11700 | 320 | 286
2026-02-01 | P03 | 11700 | 12300 | 320 | 290
2026-03-01 | P03 | 11700 | 14000 | 320 | 289
2026-04-01 | P03 | 11700 | 11900 | 320 | 275
2026-05-01 | P03 | 11700 | 11700 | 320 | 270
2026-06-01 | P03 | 11200 | 12500 | 320 | 277
2026-07-01 | P03 | 10600 | 12300 | 320 | 276
2026-08-01 | P03 | 10600 | 11700 | 320 | 274
2026-09-01 | P03 | 10600 | 11900 | 320 | 293
2025-10-01 | P04 | 16300 | 17700 | 576 | 537
2025-11-01 | P04 | 20800 | 20900 | 648 | 595
2025-12-01 | P04 | 25300 | 25400 | 720 | 705
2026-01-01 | P04 | 29700 | 29400 | 720 | 677
2026-02-01 | P04 | 32700 | 36000 | 720 | 653
2026-03-01 | P04 | 32700 | 32900 | 720 | 651
2026-04-01 | P04 | 32700 | 33900 | 720 | 654
2026-05-01 | P04 | 32700 | 35600 | 720 | 684
2026-06-01 | P04 | 31200 | 31100 | 720 | 694
2026-07-01 | P04 | 29700 | 30400 | 720 | 672
2026-08-01 | P04 | 29700 | 27600 | 720 | 652
2026-09-01 | P04 | 29700 | 29000 | 720 | 670
2025-10-01 | P05 | 4700 | 4800 | 192 | 184
2025-11-01 | P05 | 5900 | 5700 | 216 | 215
2025-12-01 | P05 | 7200 | 7800 | 240 | 238
2026-01-01 | P05 | 8500 | 8000 | 240 | 226
2026-02-01 | P05 | 9300 | 9900 | 240 | 230
2026-03-01 | P05 | 9300 | 9100 | 240 | 224
2026-04-01 | P05 | 9300 | 8700 | 240 | 238
2026-05-01 | P05 | 9300 | 8400 | 240 | 238
2026-06-01 | P05 | 8900 | 8500 | 240 | 227
2026-07-01 | P05 | 8500 | 8900 | 240 | 233
2026-08-01 | P05 | 8500 | 8600 | 240 | 232
2026-09-01 | P05 | 8500 | 8500 | 240 | 224
2025-10-01 | P06 | 8400 | 8900 | 384 | 361
2025-11-01 | P06 | 10700 | 10400 | 432 | 409
2025-12-01 | P06 | 13000 | 13800 | 480 | 421
2026-01-01 | P06 | 15300 | 14900 | 480 | 436
2026-02-01 | P06 | 16800 | 18600 | 480 | 420
2026-03-01 | P06 | 16800 | 17700 | 480 | 447
2026-04-01 | P06 | 16800 | 19800 | 480 | 447
2026-05-01 | P06 | 16800 | 18000 | 480 | 423
2026-06-01 | P06 | 16100 | 18200 | 480 | 436
2026-07-01 | P06 | 15300 | 14800 | 480 | 439
2026-08-01 | P06 | 15300 | 15900 | 480 | 428
2026-09-01 | P06 | 15300 | 16400 | 480 | 451
2025-10-01 | P07 | 8700 | 9300 | 256 | 196
2025-11-01 | P07 | 11100 | 12500 | 288 | 227
2025-12-01 | P07 | 13400 | 13500 | 320 | 243
2026-01-01 | P07 | 15800 | 17200 | 320 | 242
2026-02-01 | P07 | 17400 | 19600 | 320 | 239
2026-03-01 | P07 | 17400 | 20300 | 320 | 253
2026-04-01 | P07 | 17400 | 21000 | 320 | 243
2026-05-01 | P07 | 17400 | 19300 | 320 | 260
2026-06-01 | P07 | 16600 | 17200 | 320 | 259
2026-07-01 | P07 | 15800 | 18100 | 320 | 207
2026-08-01 | P07 | 15800 | 18100 | 320 | 211
2026-09-01 | P07 | 15800 | 18100 | 320 | 222
2025-10-01 | P08 | 3900 | 3900 | 192 | 196
2025-11-01 | P08 | 4900 | 5100 | 216 | 219
2025-12-01 | P08 | 6000 | 6500 | 240 | 249
2026-01-01 | P08 | 7000 | 6900 | 240 | 232
2026-02-01 | P08 | 7800 | 7000 | 240 | 238
2026-03-01 | P08 | 7800 | 8000 | 240 | 237
2026-04-01 | P08 | 7800 | 7900 | 240 | 247
2026-05-01 | P08 | 7800 | 7500 | 240 | 235
2026-06-01 | P08 | 7400 | 7900 | 240 | 234
2026-07-01 | P08 | 7000 | 7400 | 240 | 239
2026-08-01 | P08 | 7000 | 6700 | 240 | 239
2026-09-01 | P08 | 7000 | 7300 | 240 | 236
2025-10-01 | P09 | 12700 | 13700 | 512 | 445
2025-11-01 | P09 | 16200 | 19500 | 576 | 488
2025-12-01 | P09 | 19600 | 18800 | 640 | 552
2026-01-01 | P09 | 23100 | 26000 | 640 | 534
2026-02-01 | P09 | 25400 | 26900 | 640 | 551
2026-03-01 | P09 | 25400 | 27200 | 640 | 582
2026-04-01 | P09 | 25400 | 30500 | 640 | 545
2026-05-01 | P09 | 25400 | 27400 | 640 | 571
2026-06-01 | P09 | 24200 | 29300 | 640 | 554
2026-07-01 | P09 | 23100 | 24300 | 640 | 553
2026-08-01 | P09 | 23100 | 25400 | 640 | 580
2026-09-01 | P09 | 23100 | 24200 | 640 | 582
2025-10-01 | P10 | 15400 | 16900 | 512 | 355
2025-11-01 | P10 | 19600 | 22900 | 576 | 436
2025-12-01 | P10 | 23800 | 29600 | 640 | 439
2026-01-01 | P10 | 28000 | 35200 | 640 | 445
2026-02-01 | P10 | 30800 | 40100 | 640 | 466
2026-03-01 | P10 | 30800 | 36600 | 640 | 470
2026-04-01 | P10 | 30800 | 33600 | 640 | 447
2026-05-01 | P10 | 30800 | 36200 | 640 | 441
2026-06-01 | P10 | 29400 | 38100 | 640 | 481
2026-07-01 | P10 | 28000 | 34800 | 640 | 384
2026-08-01 | P10 | 28000 | 29800 | 640 | 402
2026-09-01 | P10 | 28000 | 33700 | 640 | 403
2025-10-01 | P11 | 10500 | 9500 | 448 | 442
2025-11-01 | P11 | 13300 | 13500 | 504 | 512
2025-12-01 | P11 | 16200 | 13900 | 560 | 594
2026-01-01 | P11 | 19000 | 18200 | 560 | 593
2026-02-01 | P11 | 21000 | 21000 | 560 | 552
2026-03-01 | P11 | 21000 | 22300 | 560 | 558
2026-04-01 | P11 | 21000 | 20500 | 560 | 561
2026-05-01 | P11 | 21000 | 21700 | 560 | 591
2026-06-01 | P11 | 20000 | 19000 | 560 | 588
2026-07-01 | P11 | 19000 | 17800 | 560 | 588
2026-08-01 | P11 | 19000 | 17800 | 560 | 565
2026-09-01 | P11 | 19000 | 20300 | 560 | 556
2025-10-01 | P12 | 7600 | 8700 | 320 | 278
2025-11-01 | P12 | 9700 | 9700 | 360 | 326
2025-12-01 | P12 | 11800 | 11300 | 400 | 353
2026-01-01 | P12 | 13900 | 13400 | 400 | 363
2026-02-01 | P12 | 15200 | 16600 | 400 | 367
2026-03-01 | P12 | 15200 | 16500 | 400 | 351
2026-04-01 | P12 | 15200 | 17000 | 400 | 364
2026-05-01 | P12 | 15200 | 15900 | 400 | 352
2026-06-01 | P12 | 14500 | 14700 | 400 | 360
2026-07-01 | P12 | 13900 | 13300 | 400 | 373
2026-08-01 | P12 | 13900 | 15400 | 400 | 371
2026-09-01 | P12 | 13900 | 15500 | 400 | 347
2025-10-01 | P13 | 13700 | 14100 | 384 | 331
2025-11-01 | P13 | 17500 | 19200 | 432 | 360
2025-12-01 | P13 | 21200 | 25100 | 480 | 411
2026-01-01 | P13 | 25000 | 26800 | 480 | 402
2026-02-01 | P13 | 27500 | 28500 | 480 | 385
2026-03-01 | P13 | 27500 | 28400 | 480 | 384
2026-04-01 | P13 | 27500 | 29300 | 480 | 391
2026-05-01 | P13 | 27500 | 27200 | 480 | 414
2026-06-01 | P13 | 26200 | 27900 | 480 | 410
2026-07-01 | P13 | 25000 | 26900 | 480 | 412
2026-08-01 | P13 | 25000 | 29700 | 480 | 390
2026-09-01 | P13 | 25000 | 28300 | 480 | 363
2025-10-01 | P14 | 9600 | 9300 | 384 | 400
2025-11-01 | P14 | 12200 | 12200 | 432 | 475
2025-12-01 | P14 | 14800 | 14700 | 480 | 512
2026-01-01 | P14 | 17500 | 14900 | 480 | 535
2026-02-01 | P14 | 19200 | 17300 | 480 | 530
2026-03-01 | P14 | 19200 | 19400 | 480 | 532
2026-04-01 | P14 | 19200 | 20000 | 480 | 530
2026-05-01 | P14 | 19200 | 20700 | 480 | 509
2026-06-01 | P14 | 18300 | 19600 | 480 | 529
2026-07-01 | P14 | 17500 | 14900 | 480 | 503
2026-08-01 | P14 | 17500 | 17700 | 480 | 533
2026-09-01 | P14 | 17500 | 14900 | 480 | 532
2025-10-01 | P15 | 5300 | 5500 | 256 | 238
2025-11-01 | P15 | 6800 | 7600 | 288 | 263
2025-12-01 | P15 | 8200 | 8000 | 320 | 307
2026-01-01 | P15 | 9700 | 10000 | 320 | 295
2026-02-01 | P15 | 10700 | 11000 | 320 | 306
2026-03-01 | P15 | 10700 | 10400 | 320 | 285
2026-04-01 | P15 | 10700 | 11300 | 320 | 306
2026-05-01 | P15 | 10700 | 10900 | 320 | 286
2026-06-01 | P15 | 10200 | 9800 | 320 | 306
2026-07-01 | P15 | 9700 | 10900 | 320 | 288
2026-08-01 | P15 | 9700 | 10300 | 320 | 284
2026-09-01 | P15 | 9700 | 9800 | 320 | 293

## Date
Month_Start | Year | Quarter | Month_Label | Month_Sort | Is_Latest_Month
2025-10-01 | 2025 | Q4 2025 | Oct 2025 | 1 | N
2025-11-01 | 2025 | Q4 2025 | Nov 2025 | 2 | N
2025-12-01 | 2025 | Q4 2025 | Dec 2025 | 3 | N
2026-01-01 | 2026 | Q1 2026 | Jan 2026 | 4 | N
2026-02-01 | 2026 | Q1 2026 | Feb 2026 | 5 | N
2026-03-01 | 2026 | Q1 2026 | Mar 2026 | 6 | N
2026-04-01 | 2026 | Q2 2026 | Apr 2026 | 7 | N
2026-05-01 | 2026 | Q2 2026 | May 2026 | 8 | N
2026-06-01 | 2026 | Q2 2026 | Jun 2026 | 9 | N
2026-07-01 | 2026 | Q3 2026 | Jul 2026 | 10 | N
2026-08-01 | 2026 | Q3 2026 | Aug 2026 | 11 | N
2026-09-01 | 2026 | Q3 2026 | Sep 2026 | 12 | Y